## Agile
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 (Sep 22 - Oct 05) | Sprint 1 | M1-1 | Design & implement database schema (User, Flight, Booking) and final user registration fields. | Must Have | None | Intern | Done
Sprint 1 (Sep 22 - Oct 05) | Sprint 1 | M1-2 | Populate database with sample flight data (100+ flights) and user accounts. | Must Have | M1-1 | Intern | Done
Sprint 2 (Oct 06 - Oct 19) | Sprint 2 | M2-1 | Build Fast APIs for flight retrieval and searching (Origin/Destination). | Must Have | M1-1 | Intern | Done
Sprint 2 (Oct 06 - Oct 19) | Sprint 2 | M2-2 | Implement dynamic pricing logic (seats, demand, time factors) and background simulation. | Must Have | M2-1 | Intern | Done
Sprint 2 (Oct 06 - Oct 19) | Sprint 2 | M2-4 | Implement input validation, sorting, and autocomplete search in the UI. | Must Have | M2-1 | Intern | Done
Sprint 3 (Oct 20 - Nov 02) | Sprint 3 | M3-1 | Implement Reserve -> Pay multi-step workflow with atomic seat reservation. | Critical | M2-4 | Intern | Done
Sprint 3 (Oct 20 - Nov 02) | Sprint 3 | M3-2 | Implement booking history retrieval and PDF ticket generation (incl. passenger name). | Must Have | M3-1 | Intern | Done
Sprint 3 (Oct 20 - Nov 02) | Sprint 3 | M3-3 | Implement ticket cancellation, partial refund, and record archival to audit log. | Should Have | M3-1 | Intern | Done
Sprint 4 (Nov 03 - Nov 22) | Sprint 4 | M4-1 | Finalize UI polish (Aesthetic, Layout, Footer) and ensure seamless API connectivity. | Must Have | M3-3 | Intern | Done
Sprint 4 (Nov 03 - Nov 22) | Sprint 4 | M4-2 | Integrate AI Chatbot (Gemini API) for trip planning utility and fix payment/history flow. | Should Have | M4-1 | Intern | Done
Sprint 4 (Nov 03 - Nov 22) | Sprint 4 | M4-3 | Final project testing and successful deployment to render. | Must Have | M4-2 | Intern | Done