## Defect_Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Intern | 2025-09-29 | Error: table user has no column named profile_data during DB initialization. | Sprint 1 | Intern | Standards | Cleaned db.sql by dropping all tables and correcting INSERT statements to use full_name, phone, country schema. | 2025-09-29 | Closed | Fixed schema migration error.
2 | Intern | 2025-10-05 | KeyError: 'demand_factor' when fetching flights. | Sprint 2 | Intern | Integration | Added demand_factor column via ALTER TABLE to resolve schema mismatch. | 2025-10-05 | Closed | Backend logic fix.
3 | Intern | 2025-10-07 | Price display in search results table shows two overlapping currency values. | Sprint 2 | Intern | User Interface | Consolidated multiple st.write() calls in the price column to a single, formatted output. | 2025-10-07 | Closed | UI rendering artifact resolved.
4 | Intern | 2025-10-12 | AttributeError: 'NoneType' object has no attribute 'get' when canceling a pending booking. | Sprint 2 | Intern | Runtime | Added if cancel_result: check to safely handle None return from api_request. | 2025-10-12 | Closed | Frontend API response handling issue.
5 | Intern | 2025-10-14 | Autocomplete select boxes fail to load the full list of airport destinations reliably. | Sprint 2 | Intern | User Interface | Verified fetch_airports uses api_request with method='GET' correctly. | 2025-10-14 | Closed | API call integration verified.
6 | Intern | 2025-10-18 | Payment not confirming due to hardcoded user_id=1 in POST /bookings. | Sprint 3 | Intern | Data Logic | Updated BookingRequest and POST /bookings to receive and use the dynamic user_id from the frontend session. | 2025-10-18 | Closed | Resolved critical user ID mismatch.
7 | Intern | 2025-10-21 | Confirmed bookings not visible in history due to status filter (CONFIRMED). | Sprint 3 | Intern | Logical | Updated GET /bookings/history to use the robust SQL filter: UPPER(b.status) LIKE '%CONFIRMED%'. | 2025-10-21 | Closed | Fixed SQL case-sensitivity error.
8 | Intern | 2025-10-24 | Clicking "Book Now" in search results disappears immediately (state reset). | Sprint 3 | Intern | User Interface | Reworked "Book Now" logic using stable st.form + st.selectbox pattern to guarantee state transfer (autofill_flight_id). | 2025-10-24 | Closed | Fixed Streamlit session state leak on interaction.
9 | Intern | 2025-10-25 | Final PDF ticket uses the username instead of the user's first name + last name. | Sprint 3 | Intern | Data Logic | Updated POST /bookings to save passenger_full_name and updated generate_ticket_pdf to use this new column. | 2025-10-25 | Closed | Ticket generation fidelity ensured.
10 | Intern | 2025-10-26 | Cancellation endpoint returns Operation Failed: Method Not Allowed. | Sprint 3 | Intern | Integration | Updated frontend.py to use api_request(..., method='DELETE') instead of method='POST' for cancellation. | 2025-10-26 | Closed | Fixed incorrect HTTP method call.
11 | Intern | 2025-11-01 | Initial UI Banner Image does not use the correct compatible parameter. | Sprint 4 | Intern | Standards | Replaced deprecated use_column_width with use_container_width=True in st.image calls. | 2025-11-01 | Closed | Fixed deprecation warning.
12 | Intern | 2025-11-03 | AI Chatbot fails with Gemini API key not configured on server. | Sprint 4 | Intern | Configuration | Verified GEMINI_API_KEY was set as an environment variable in the terminal session before running uvicorn. | 2025-11-03 | Closed | Resolved environment configuration failure.
13 | Intern | 2025-11-06 | User registration form shows password and username but is missing new fields (Name, Phone, Country). | Sprint 4 | Intern | User Interface | Updated the registration form HTML elements in frontend.py to include inputs for full_name, phone, and country. | 2025-11-06 | Closed | UI updated to reflect new schema fields.
14 | Intern | 2025-11-09 | ArrowInvalid crash in search results caused by PyArrow trying to convert currency to float. | Sprint 4 | Intern | Serialization | Applied .astype(str) conversion to all currency columns in display_flights_data and history tables. | 2025-11-09 | Closed | Fixed PyArrow/Pandas serialization crash.
15 | Intern | 2025-11-12 | Domestic/International flight list filter is not working correctly. | Sprint 4 | Intern | Data Logic | Debugged Python filter logic to ensure ', India' check is applied correctly to both from and to fields. | 2025-11-12 | Closed | Fixed Python string matching error.
16 | Intern | 2025-11-15 | Footer overlaps with the bottom of long pages (small screens). | Sprint 4 | Intern | User Interface | Added custom CSS to fix footer position and increased padding-bottom in the main container to prevent overlap. | 2025-11-15 | Closed | Fixed layout overlap.
17 | Intern | 2025-11-17 | Search form logic fails when user uses the Selectbox after typing in the input box (interaction conflict). | Sprint 4 | Intern | User Interface | Simplified the search input on the landing page to rely only on two select boxes (st.selectbox) instead of complex typing/filtering combination. | 2025-11-17 | Closed | Fixed interaction conflict on landing page.
18 | Intern | 2025-11-19 | When navigating to History/Cancel, the tab often defaults to "Cancellation History" even if no records exist. | Sprint 4 | Intern | User Interface | Ensured the initial active tab logic prioritizes "Confirmed Bookings" if any data exists. | 2025-11-19 | Closed | Improved UI default state.
19 | Intern | 2025-11-21 | Final check of links shows Refund Receipt Download button is giving an internal error. | Sprint 4 | Intern | Runtime | Verified DELETE endpoint correctly fetches data needed for receipt PDF before deletion; fixed minor SQL variable in DELETE handler. | 2025-11-21 | Closed | Final check on API links.
20 | Intern | 2025-11-22 | Final deployment check on render results in slow startup due to large initial data fetch. | Sprint 4 | Intern | Standards | Verified requirements.txt is minimal and confirmed the use of st.cache could be added later for static API fetches. | 2025-11-22 | Closed | Final deployment verification.